## Sheet4
Activity ID | Pred/Succ Report ID | Activity Name | Original Duration | Start | Finish | Predecessors | Successors
Microstructural Scale Fuel Performance Modeling |  |  | 1772d | 10-01-18 A | 2025-10-01
FY20 |  |  | 254d | 2019-10-01 | 2020-09-30
A63415 |  | INL Microstructural Modeling - FY20 Gas Diffusivity in Different Phases (INL) | 254d | 2019-10-01 | 2020-09-30 | A63315 | A63555, A63510 FF |  | 125
A63435 |  | INL Microstructural Modeling - FY20 Irradiation Enhanced Creep (PNNL) | 254d | 2019-10-01 | 2020-09-30 | A63335 | A63540, A63510 FF |  |  |  | 250
A63445 |  | INL Microstructural Modeling - FY20 Effects of Carbides in Fuel Integrity (ANL) | 254d | 2019-10-01 | 2020-09-30 | A63365 | A63615, A63555, A63510 FF | [5 empty] | 100
A63465 |  | INL Microstructural Modeling - FY20 Property Degradation: Elasticity (INL) | 254d | 2019-10-01 | 2020-09-30 | A63365 | A63525, A63510 FF |  | 100
A63480 |  | INL Microstructural Modeling - FY20 Property Degradation: Thermal Conductivity (INL) | 254d | 2019-10-01 | 2020-09-30 | A63365 | A63585, A63510 FF |  | 125
A63495 |  | INL Microstructural Modeling - FY20 Integration of Microstructural Modeling into Fuel Performance Modeling (ANL) | 254d | 2019-10-01 | 2020-09-30 | A63300, A63285, A63345, A63195, A63165 | A63600, A63570, A63510 FF | [5 empty] | 100
A63500 | NEW ACTIVITY | INL Historical Samples Characterization Data Assessment (INL) (FY20) | 254d | 2019-10-01 | 2020-09-30 | A63380 | A63505 FF, A63620 |  | 60
A63505 | NEW ACTIVITY | INL Historical Samples Characterization Data Assessment Report Input (INL) (FY20) | 43d | 2020-07-31 | 2020-09-30 | A93910 | A63510 FF |  | 20
A63510 |  | INL Microstructural Modeling - FY20 Complete Microstructural Modeling Summary Report (INL) | 43d | 2020-07-31 | 2020-09-30 | A63495 FF, A63480 FF, A63465 FF, A63445 FF, A63435 FF, A63415 FF, A63505 FF | A29200 FF |  | 30 |  | 10 |  | 10
[8 empty] | INL | 460 | PNNL | 260 | ANL | 210 | TOTAL | 930
FY21 |  |  | 253d | 2020-10-01 | 2021-09-30
A63525 |  | INL Microstructural Modeling - FY21 Degradation in Fracture Stress at Interaction Layers (INL) | 253d | 2020-10-01 | 2021-09-30 | A63465 | A63645, A63630 FF |  | 75
A63540 |  | INL Microstructural Modeling - FY21 Irradiation Enhanced Creep (PNNL) | 253d | 2020-10-01 | 2021-09-30 | A63435 | A63690, A63630 FF |  |  |  | 250
A63555 |  | INL Microstructural Modeling - FY21 Effects of Carbides in Fuel Integrity (ANL) | 253d | 2020-10-01 | 2021-09-30 | A63445, A63415 | A63675, A63660, A63630 FF | [5 empty] | 100
A63570 |  | INL Microstructural Modeling - FY21 Fuel Qualification Support: Assessment of Swelling at Various Fission Rates (ANL) | 253d | 2020-10-01 | 2021-09-30 | A63495 | A63690, A63630 FF | [5 empty] | 100
A63585 |  | INL Microstructural Modeling - FY21 Property Degradation: Thermal Conductivity (INL) | 253d | 2020-10-01 | 2021-09-30 | A63480 | A63720, A63630 FF |  | 125
A63600 |  | INL Microstructural Modeling - FY21 Integration of Microstructural Modeling into Fuel Performance Modeling (INL) | 253d | 2020-10-01 | 2021-09-30 | A63495 | A63720, A63705, A63630 |  | 100
A63615 |  | INL Microstructural Modeling - FY21 Effect of U-235 Enrichment in Carbides (ANL) | 253d | 2020-10-01 | 2021-09-30 | A63445 -Change PREDS TO INL | A63735, A63690, A63630 FF - CHANGE SUCC TO INL | [5 empty] | 100
A63620 | NEW ACTIVITY | INL Historical Samples Characterization Data Assessment (INL) (FY21) | 253d | 2020-10-01 | 2021-09-30 | A93910 | A63621 FF, A63740 |  | 60
A63621 | NEW ACTIVITY | INL Historical Samples Characterization Data Assessment Report Input (INL) (FY21) | 42d | 2021-08-03 | 2021-09-30 | A63620 FF | A63630 FF |  | 20
A63630 |  | INL Microstructural Modeling - FY21 Complete Microstructural Modeling Summary Report (INL) | 43d | 2021-08-02 | 2021-09-30 | A63615 FF, A63600 FF, A63585 FF, A63570 FF, A63555 FF, A63540 FF, A63525 FF, A63621 FF | A29230 FF |  | 30 |  | 10 |  | 10
[8 empty] | INL | 410 | PNNL | 260 | ANL | 310 | TOTAL | 980
FY22 |  |  | 253d | 2021-10-01 | 2022-09-30
A63645 |  | INL Microstructural Modeling - FY22 Degradation in Fracture Stress at Interaction Layers (INL) | 253d | 2021-10-01 | 2022-09-30 | A63525 | A63765 FF |  | 75
A63660 |  | INL Microstructural Modeling - FY22 Effects of Impurities on Fuel Performance: Si and Al (INL) | 253d | 2021-10-01 | 2022-09-30 | A63555 | A63810, A63795, A63780, A63765 FF |  | 75
A63675 |  | INL Microstructural Modeling - FY22 Effects of Impurities on Fuel Performance: Si and Al (PNNL) | 253d | 2021-10-01 | 2022-09-30 | A63555 | A63810, A63795, A63780, A63765 FF |  |  |  | 100
A63690 |  | INL Microstructural Modeling - FY22 Fuel Qual Support: Assessment of Swelling w/ Different Fab Microstructure (PNNL) | 253d | 2021-10-01 | 2022-09-30 | A63540, A63615, A63570 | A63825, A63765 FF |  |  |  | 100
A63705 |  | INL Microstructural Modeling - FY22 Comparison to MP-1 Experiments: Uncertainty Analysis (ANL) | 253d | 2021-10-01 | 2022-09-30 | A63600 | A63855, A63840, A63765 FF | [5 empty] | 50
A63720 |  | INL Microstructural Modeling - FY22 Integration of the Effect of U-235 Uniformity on Swelling into Fuel Perf Model (ANL) | 253d | 2021-10-01 | 2022-09-30 | A63600, A63585 | A63765 FF | [5 empty] | 100
A63735 |  | INL Microstructural Modeling - FY22 Effect of U235 Enrichment in Carbides (ANL) | 253d | 2021-10-01 | 2022-09-30 | A63615 | A63810, A63795, A63780, A63765 FF | [5 empty] | 100
A63740 | NEW ACTIVITY | INL MP-1 Samples Characterization Data Assessment (INL) (FY22) | 253d | 2021-10-01 | 2022-09-30 | A63620 | A63745, A63860 |  | 60
A63745 | NEW ACTIVITY | INL MP-1 Characterization Data Assessment Report Input (INL) (FY22) | 42d | 2022-08-03 | 2022-09-30 | A63740 | A63765 FF |  | 20
A63765 | New Title | INL Microstructural Modeling - MP-1 Complete Microstructural Modeling Summary Report (INL) | 44d | 2022-08-01 | 2022-09-30 | A63735 FF, A63720 FF, A63705 FF, A63690 FF, A63675 FF, A63660 FF, A63645 FF, A63745 FF | A29241 FF, A29250 FF |  | 30 |  | 10 |  | 10
[8 empty] | INL | 260 | PNNL | 210 | ANL | 260 | TOTAL | 730
FY23 |  |  | 253d | 2022-10-03 | 2023-10-02
A63780 |  | INL Microstructural Modeling - FY23 Effects of Impurities on Fuel Performance: Other Impurities (INL) | 252d | 2022-10-03 | 2023-09-29 | A63735, A63675, A63660 | A64080, A64065, A64050, A63945 FF |  | 70
A63795 |  | INL Microstructural Modeling - FY23 Effects of Impurities on Fuel Performance: Other Impurities (PNNL) | 252d | 2022-10-03 | 2023-09-29 | A63675, A63735, A63660 | A64080, A64065, A64050, A63945 FF |  |  |  | 65
A63810 |  | INL Microstructural Modeling - FY23 Effects of Impurities on Fuel Performance: Other Impurities (ANL) | 252d | 2022-10-03 | 2023-09-29 | A63735, A63675, A63660 | A64080, A64065, A64050, A63945 FF | [5 empty] | 65
A63825 |  | INL Microstructural Modeling - FY23 Fuel Qualification Support: Fuel Coolability and Mechanical Integrity (INL) | 252d | 2022-10-03 | 2023-09-29 | A63690 | A64080, A64065, A64050, A63945 FF, A63890 |  | 100
A63840 |  | INL Microstructural Modeling - FY23 Comparison to MP-1 Experiments: Model Calibration (ANL) | 252d | 2022-10-03 | 2023-09-29 | A63705 | A63945 FF | [5 empty] | 25
A63855 |  | INL Microstructural Modeling - FY23 Comparison to MP-1 Experiments: Model Calibration (PNNL) | 252d | 2022-10-03 | 2023-09-29 | A63705 | A63945 FF |  |  |  | 25
A63860 | A63750 | INL MP-1 Samples Characterization Data Assessment (INL) (FY23) [Keep old title: INL MP-1 Fuel Qualification Sample Data Assessment (INL) (FY23)] | 253d | 2022-10-03 | 2023-09-29 | A63740 | A63865, A63895 |  | 60
A63865 | A63930 | INL MP-1 Samples Characterization Data Assessment Report Input (INL) (FY23) [Keep old title: INL MP-1 Fuel Qualification Sample Data Assessment Summary Report (INL) (FY23)] | 42d | 2023-08-03 | 2023-09-29 | A63860 | A63945 FF |  | 20
A63945 |  | INL Microstructural Modeling - FY23 MP-1 Complete Microstructural Modeling Summary Report (INL) | 43d | 2023-08-02 | 2023-09-29 | A63855 FF, A63840 FF, A63825 FF, A63810 FF, A63795 FF, A63780 FF, A63865 FF | A29250 FF, A63885, A63870 |  | 30 |  | 10 |  | 10
[8 empty] | INL | 280 | PNNL | 100 | ANL | 100 | TOTAL | 480
FY24 |  |  | 253d | 2023-10-03 | 2024-10-01
A63870 |  | INL Microstructural Modeling - FY24 Comparison to MP-2 Experiments: Uncertainty Analysis (ANL) | 253d | 2023-10-03 | 2024-09-30 | A63945 | A63990, A63975, A63960 | [5 empty] | 25
A63885 |  | INL Microstructural Modeling - FY24 Comparison to MP-2 Experiments: Uncertainty Analysis (PNNL) | 253d | 2023-10-03 | 2024-09-30 | A63945 | A63990, A63975, A63960 |  |  |  | 25
A63890 |  | INL Microstructural Modeling - FY24 Fuel Qualification Support: Fuel Coolability and Mechanical Integrity (INL) | 252d | 2023-10-04 | 2024-09-30 | A63825, A63898 | A63990, A63975, A63960 |  | 100
A63895 | A64110 | INL MP-2 Samples Characterization Data Assessment (INL) (FY24) [Keep old title but change the fiscal year to FY24: INL MP-2 Fuel Qualification Sample Data Assessment (INL) (FY24)] | 253d | 2023-10-03 | 2024-09-30 | A63860 | A63898 FF, A63968 |  | 60
A63898 | A64125 | INL MP-2 Samples Characterization Data Assessment Report Input (INL) (FY24) [Keep old title: INL MP-2 Fuel Qualification Sample Data Assessment Summary Report (INL) (FY25)] | 42d | 2024-08-02 | 2024-09-30 | A63895 FF | A63890 FF |  | 20
NEW 1 |  | INL Microstructural Modeling - FY24 MP-1 Complete Microstructural Modeling Summary Report (INL) | 43d | 2024-08-02 | 2024-09-30 | Add PREDs | ADD SUCC |  | 30
[8 empty] | INL | 210 | PNNL | 25 | ANL | 25 | TOTAL | 260
FY25 |  |  | 1625d | 2019-05-01 | 2025-10-01
A63960 |  | INL Microstructural Modeling - FY25 Comparison to MP-2 Experiments: Model Calibration (INL) | 130d | 2024-10-02 | 2025-04-08 | A63885, A63870, A63890 | A64140 FF, A64080 FF, A64065 FF, A64050 FF |  | 25
A63968 | NEW ACTIVITY | INL MP-2 Samples Characterization Data Assessment (INL) (FY25) | 130d | 2024-10-02 | 2025-04-08 | A63895 | A63970 FF |  | 60
A63970 | NEW ACTIVITY | INL MP-2 Samples Characterization Data Assessment Report Input (INL) (FY25) | 42d | 2025-02-10 | 2025-04-08 | A63968 FF | A64140 FF |  | 20
A63900 | DELETE | INL Microstructural Modeling - FY23 Comparison to MP-ATR Experiments: Uncertainty Analysis (ANL)
A63915 | DELETE | INL Microstructural Modeling - FY23 Comparison to MP-ATR Experiments: Uncertainty Analysis (PNNL)
A63975 |  | INL Microstructural Modeling - FY25 Comparison to MP-2 Experiments: Model Calibration (ANL) | 130d | 2024-10-02 | 2025-04-08 | A63885, A63870, A63890 | A64080 FF, A64065 FF, A64050 FF |  |  |  | 25
A63990 |  | INL Microstructural Modeling - FY25 Comparison to MP-2 Experiments: Model Calibration (PNNL) | 130d | 2024-10-02 | 2025-04-08 | A63885, A63870, A63890 | A64080 FF, A64065 FF, A64050 FF | [5 empty] | 25
A64005 |  | INL Microstructural Modeling - FY25 Comparison to MP-ATR Experiments: Model Calibration (INL) | 123d | 2025-04-09 | 2025-09-30 | A64050 | A64145 FF |  | 25
A64015 | NEW ACTIVITY | INL MP-ATR Samples Characterization Data Assessment (INL) (FY25) | 123d | 2025-04-09 | 2025-09-30 | A64050 | A64038 FF |  | 60
A64020 |  | INL Microstructural Modeling - FY25 Comparison to MP-ATR Experiments: Model Calibration (ANL) | 123d | 2025-04-09 | 2025-09-30 | A64080 | A64145 FF |  |  |  | 25
A64035 |  | INL Microstructural Modeling - FY25 Comparison to MP-ATR Experiments: Model Calibration (PNNL) | 123d | 2025-04-09 | 2025-09-30 | A64065 | A64145 FF | [5 empty] | 25
A64038 | New Activity | INL MP-ATR Samples Characterization Data Assessment Report Input (FY25) | 42d | 2025-08-04 | 2025-09-30 | A64015 FF | A64145 FF |  | 20
A64050 |  | INL Microstructural Modeling - FY25 Fuel Qual Support: Integrated Assessment & Assessment Report (INL) | 41d | 2025-02-11 | 2025-04-08 | A63990 FF, A63975 FF, A63960 FF, A63825, A63810, A63795, A63780 | A64155, A30500 FF 44d, A64005, A64015 |  | 25
A64065 |  | INL Microstructural Modeling - FY25 Fuel Qual Support: Integrated Assessment & Assessment Report (PNNL) | 41d | 2025-02-11 | 2025-04-08 | A63990 FF, A63975 FF, A63960 FF, A63825, A63810, A63795, A63780 | A64155, A30500 FF 44d, A64035 |  |  |  | 25
A64080 |  | INL Microstructural Modeling - FY25 Fuel Qual Support: Integrated Assessment & Assessment Report (ANL) | 41d | 2025-02-11 | 2025-04-08 | A63990 FF, A63975 FF, A63960 FF, A63825, A63810, A63795, A63780 | A64155, A30500 FF 44d, A64020 | [5 empty] | 25
A64140 |  | INL Microstructural Modeling Summary Report Post MP-2 Assessment (INL) | 42d | 2025-02-10 | 2025-04-08 | A63960FF, A63970 FF, A63965 FF | A64155 |  | 30
A64145 | New Activity | INL Microstructural Modeling - FY25 MP-ATR Complete Microstructural Modeling Summary Report (INL) | 63d | 2025-07-03 | 2025-09-30 | A64020 FF, A64035 FF, A64005 FF, A64038 FF | A64155 |  | 30
A64155 | A64095 | INL-Microstructural Modeling Complete - FY25 | 0d |  | 2025-09-30 | A64140, A64125, A64080, A64050, A64065, A64145 | A30660 FF |  | 0
[8 empty] | INL | 295 | PNNL | 75 | ANL | 75 | TOTAL | 445
Note on K12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: split this task into lab-specific roles
Note on C20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: verify these two tasks. A63600 is now @ INL, A63615 is @ ANL
Note on K24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: task split into 3 labs
Note on K36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: split into 3 labs
Note on K39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: is this a 200K total task split into 3 labs? if so, great. just checking
Note on O42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: after review… I would like to split this task into 3. 50k INL, 25k PNNL, 25k ANL
Note on K47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: split into 3 labs
Note on O52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: same for this task, split into 3. 50k INL, 25k PNNL, 25k ANL