## Active
Work Package Title | LWBS | Activity ID | Activity Name | PM | PI | Monthly Input
23.1.1.1.1.1.1 |  |  | Monolithic Base Fuel Qualification
Mini Plate 1 (MP-1) | 22.18 | A20250 | MP-1 Perform Fresh Fuel Microstructural Characterization | Meacham N | Marshall M/Jue, J | 03/06/19 • The first fuel plate (A1B103) has been re-polished for optical microscopy analysis. After review of the preliminary SEM data from the second fuel plate (A1C174), more detailed SEM characterization on several microstructural features will be performed on this fuel plate. Two more fuel plates (A2B101 and A2C108) have been sectioned and mounted. Sample preparation for SEM characterization is underway.
Mini Plate 1 (MP-1) | 22.18 | A20403 | MP-1 Pre-Irradiation Material Properties Bond Strength | Meacham N | Marshall M/Smith, J | 1/7/19 • Six (6) of the ten (10) laser shock test on MP-1 LEU plates was completed.
Mini Plate 1 (MP-1) | 22.18 | A20405 | MP-1 Pre-Irradiation Material Properties Residual Stress (HEU) | Meacham N | Marshall M/Schulthess, J
Mini Plate 1 (MP-1) | 22.18 | A20454 | MP-1 Capsule Loading QA - (HP) | Meacham N | Marshall M/Robinson, A. | 1/7/19 Concern/Issue: Any delays with HEU fuel fabrication at BWXT will delay high power capsule loading. It also has the potential to impact the remaining MP-1 HEU fresh fuel characterization and material properties testing.
Mini Plate 1 (MP-1) | 22.18 | A20500 | MP-1 LP Irradiation (6 Cycles) - Large B | Meacham N | Glagolenko I / Marshall M | 03/06/19 • Completed visual examination and channel gap measurements of four Low Power (LP) capsules (B-10) in February. The results of the measurements will be compared to the projected data results.
Mini Plate 1 (MP-1) | 22.18 | A20505 | MP-1 MP Irradiation (5 Cycles) - SFT | Meacham N | Glagolenko I / Marshall M | 03/06/19 • Completed visual examination and channel gap measurements of four Medium Power (MP) capsules (SFT) in February. The results of the measurements will be compared to the projected data results.
Mini Plate 1 (MP-1) | 22.18 | A20505A | MP-1 MP Irradiation (5 Cycles) - SFT (Adjustment Jan 2019) | Meacham N
Mini Plate 1 (MP-1) | 22.18 | A20550 | MP-1 Final As-Run Analysis | Meacham N | Glagolenko I / Marshall M | 03/06/19 • Final as-run analysis will not be completed until the final/ irradiation of each power level of the capsule. Initial work has commenced in the form of cycle-by-cycle analysis of B-12 and B-10 low power first cycle irradiations as well as the first cycle irradiation of the medium power test in the SFT.
Mini Plate 1 (MP-1) | 22.18 | A20600 | MP-1 Cooling and Shipping LP | Meacham N | Glagolenko I / Marshall M | 03/06/19 • MP-1 Cooling and Shipping LP continues. The four B-12 capsules were shipped to MFC in December 2018. The four B-10 capsules are cooling in the ATR canal with a shipment scheduled for May 2019. Shipment specific isotopic and thermal engineering calculations and analysis reports (ECARS) are in development to support the upcoming shipment.
Mini Plate 1 (MP-1) | 22.18 | A20610 | MP-1 Cooling and Shipping MP | Meacham N | Glagolenko I / Marshall M | 03/06/19 • Two medium power capsules (M2 & M4) are cooling in the ATR canal with a shipment scheduled for May 2019. Shipment specific isotopic and thermal ECARS are in development to support the upcoming shipment. The two MP capsules are planned to ship with the four LP capsules in May 2019.
Mini Plate 1 (MP-1) | 22.18 | A20620 | MP-1 HFEF PIE Equipment Preparations | Meacham N | Marshall M/Robinson, A. | 11/29/18 “lots of big accomplishments” [1] [1] Personal communication with A.B. Robinson, Nov. 29, 2018.
Mini Plate 1 (MP-1) | 22.18 | A20621 | MP-1 HFEF PIE Equipment Preparations - Complete | Meacham N | Marshall M/Robinson, A.
Mini Plate 1 (MP-1) | 22.18 | A20690 | MP-1 Non-Destructive PIE MP | Meacham N | Marshall M/Robinson, A.
Mini Plate 1 (MP-1) | 22.18 | A20700 | MP-1 Non-Destructive PIE LP | Meacham N | Marshall M/Robinson, A. | 03/06/19 • All 14 plates from the four MP-1 LP B-10 capsules have completed neutron radiography. These plates will begin immersion density measurements followed by Precision Gamma Scanning.
Full Size Plate 1 (FSP-1) | 22.16 | A23350 | FSP-1 Final Design Review (INL) |  | Marshall M | 03/06/19 • The FSP-1 Final Design Review commenced in February and is planned to be completed in May 2019.
Full Size Plate 1 (FSP-1) | 22.16 | A23351 | FSP-1 Final Design Review (INL) - Complete | Meacham N | Marshall M
Mini Plate 2 (MP-2) | 22.24 | A24652 | MP-2 Preliminary Design | Meacham N | Glagolenko I / Marshall M | 03/06/19 • Continued preliminary design for each MP-2 ATR irradiation position (B-9, B-11, B-12, I-12, I-24, SFT). • Developed comprehensive MP-2 physics and thermal/hydraulic models based on designed test configuration including specific plate and capsule matrix for each reactor peak power and burnup targets. • Developing programmatic ECARs including physics, thermal/hydraulic, and structural documenting programmatic objectives can be achieved. • Developing bounding safety ECARs including physics, thermal/hydraulic, and structural documenting the experiment can be executed within the safety basis of the ATR. • Developing experiment design drawings including five different MP-2 plate and foil geometries, capsules, flux wires, irradiation vehicles, experiment handling tools, shipping hardware, and experiment assembly. • Developing new fuel specification and test plan to support fuel fabrication (FF) pillar fabrication control plan and fuel fabrication contract with BWXT.
Mini Plate 2 (MP-2) | 22.24 | A24652A | MP-2 Preliminary Design (Adjustment Jan 2019) | Meacham N
Mini Plate 2 (MP-2) | 22.24 | A24653 | MP-2 Preliminary Design Review | Meacham N | Glagolenko I / Marshall M
Mini Plate 2 (MP-2) | 22.24 | A24654 | MP-2 Preliminary Design Review - Complete | Meacham N | Glagolenko I / Marshall M
Mini Plate 2 (MP-2) | 22.24 | A24670 | MP-2 Test Plan & Fuel Specification (Preliminary Design) | Meacham N | Glagolenko I / Marshall M | 2/6/19 • “Fuel Specification for MP-1, MP-2, and FSP-1 Specification” (SPC-1691), Revision 5 was distributed for review. • “Mini-Plate Two (MP-2) Irradiation Test Campaign Experiment Execution Plan” (PLN-5415) was updated to include updated experiment methodology and design. Scheduling and project management sections still need to be updated.
Mini Plate 2 (MP-2) | 22.24 | A24671 | MP-2 Test Plan & Fuel Specification (Preliminary Design) - Complete | Meacham N | Glagolenko I / Marshall M
Mini Plate 2 (MP-2) | 22.24 | A24756 | MP-2 Final Design | Meacham N | Glagolenko I / Marshall M
Element Test 1 (ET-1) | 22.25 | A25925 | ET-1 Prepare Experiment Test Plan | Kunz TJ | Cole J / Glagolenko I | 03/06/19 • A contract was awarded with MPR to complete the ET-1 Test Plan.
Element Test 1 (ET-1) | 22.25 | A25926 | ET-1 Prepare Experiment Test Plan - Complete | Kunz TJ | Cole J / Glagolenko I
Element Test 1 (ET-1) | 22.25 | A25930 | ET-1 Element Test Fuel Design | Kunz TJ | Cole J / Glagolenko I
Fuel Product Specifications | 22.23 | A29000 | Complete Product Specification Report Rev 11 | Kunz TJ | Brower J | 03/06/19 • Comments have been incorporated into draft revisions of FOR-158, SPC-1635, TEV-2009. The documents have been sent to INL Document Management for editing. Revisions will be issued by March 31, 2019 to meet the DOE milestone.
Fuel Product Specifications | 22.23 | A29001 | Complete Product Specification Report Rev 11 - Complete | Kunz TJ | Brower J
Fuel Product Specifications | 22.23 | A29050 | Complete Product Specification Report Rev 12 | Kunz TJ | Brower J
Fuel Product Specifications | 22.23 | A29051 | Complete Product Specification Report Rev 12 - Complete | Kunz TJ | Brower J
Base Fuel Qualification Report | 22.14 | A29841 | Document and Track Fuel Qualification Requirements (DOORS) FY19 | Johnson MP | Cole J | 2/28/19 • Continue to obtain FQ test plan numbers from Experiment and Work Package Managers. M. Johnson
Base Fuel Qualification Report | 22.14 | A29842 | Document and Track Fuel Qualification Requirements (DOORS) FY19 - Complete | Johnson MP | Cole J | 2/28/19 Milestone On Track, M. Johnson
Base Fuel Qualification Report | 22.14 | A29856 | Update Fuel Performance Qualification Data Management (NDMAS) FY19 | Johnson MP | Cole J | 2/28/19 • Continue to work webpage views to include MP-1 data. M. Johnson
Base Fuel Qualification Report | 22.14 | A29857 | AFIP 7 Review Flow Test Data | Johnson MP | Cole J | 2/28/19 • Planned to start April 2019, M. Johnson
Base Fuel Qualification Report | 22.14 | A29859 | Update Fuel Performance Qualification Data Management (NDMAS) FY19 - Complete | Johnson MP | Cole J | 2/28/19 Milestone On Track, M. Johnson
Base Fuel Qualification Report | 22.14 | A30300 | Annual Base Fuel Qualification Report (FY19) | Johnson MP | Cole J | 03/06/19 • The structure and layout of the report continues to be determined.
Base Fuel Qualification Report | 22.14 | A30301 | Annual Base Fuel Qualification Report (FY19) - Complete | Johnson MP | Cole J | 2/28/19 Milestone On Track, M. Johnson
23.1.1.1.1.1.2 |  |  | Monolithic Base Fuel Demonstrations
MITR Design Demonstration Experiment (DDE) | 23.01 | A30850 | BEA/SCK - MITR DDE Conceptual Design | Jacobson JD | Jones W | 03/06/19 • The experiment F&OR is progressing. • A process diagram was developed for INL-based experiments which are irradiated and examined at BR2. This will be vetted with the BR2 team over the next month.
MITR Design Demonstration Experiment (DDE) | 23.01 | A30855 | BEA - Prepare SOW for MITR DDE Experiment | Jacobson JD | Jones W | 03/06/19 • Scope requirements are being defined and will be separated into work performed by SCK-CEN and BEA.
MITR Design Demonstration Experiment (DDE) | 23.01 | A30865 | BEA - Award SCK Contract for MITR DDE | Jacobson JD | Jones W | 2/26/19 not started
MITR Design Demonstration Experiment (DDE) | 23.01 | A31000 | BEA/SCK - MITR DDE Conceptual Design Review | Jacobson JD | Jones W | 2/26/19 not started
MITR Design Demonstration Experiment (DDE) | 23.01 | A31025 | BEA - MITR DDE Fuel Spec (Conceptual) | Jacobson JD | Jones W | 03/06/19 • The conceptual Fuel Specification is under development. Input is being provided for the SPC 1691 revision.
MITR Design Demonstration Experiment (DDE) | 23.01 | A31050 | BEA/SCK - MITR DDE Preliminary Design | Jacobson JD | Jones W | 2/26/19 not started
MURR Design Demonstration Experiment (DDE) | 23.02 | A32300 | MURR DDE Conceptual Design | Jacobson JD | Glagolenko, I | 03/06/19 • Neutronics has begun.
NBSR Design Demonstration Experiment (DDE) | 23.03 | A33850 | BEA/SCK - NBSR DDE Conceptual Design | Jacobson JD | Jones W | 03/06/19 • The experiment F&OR is progressing. • A process diagram was developed for INL-based experiments which are irradiated and examined at BR2. This will be vetted with the BR2 team over the next month.
NBSR Design Demonstration Experiment (DDE) | 23.03 | A33855 | BEA - BEA - Prepare SOW for NBSR DDE Experiment | Jacobson JD | Jones W | 03/06/19 • Scope requirements are being defined and will be separated into work performed by SCK-CEN and INL.
NBSR Design Demonstration Experiment (DDE) | 23.03 | A33865 | BEA - Award SCK Contract for NBSR DDE | Jacobson JD | Jones W | 2/26/19 not started
NBSR Design Demonstration Experiment (DDE) | 23.03 | A34000 | BEA/SCK - NBSR DDE Conceptual Design Review | Jacobson JD | Jones W | 2/26/19 not started
NBSR Design Demonstration Experiment (DDE) | 23.03 | A34025 | BEA- NBSR DDE Fuel Spec (Conceptual) | Jacobson JD | Jones W | 03/06/19 • The conceptual Fuel Specification is under development. Input is being provided for the SPC-1691 revision.
NBSR Design Demonstration Experiment (DDE) | 23.03 | A34050 | BEA/SCK - NBSR DDE Preliminary Design | Jacobson JD | Jones W | 2/26/19 not started
BR2 Capability Development | 23.06 | A37010 | INL/SCK-Mustang R & P Conceptual Design | Hammond MR | Jones W | 3/6/19 • The logic associated with this activity has changed. Conceptual design directly ties to completing CEE-II in FY20. The conceptual design task for MUSTANG-R & P will continue through the remainder of the fiscal year.
BR2 Capability Development | 23.06 | A37015 | SCK- Submit Long Lead Procurement Summary & Procure Materials | Hammond MR | Jones W | 2/28/19 • On schedule for submittal at end of March.
BR2 Capability Development | 23.06 | A37020 | INL/SCK- Submit Preliminary QA Approach to BEA | Hammond MR | Jones W | 2/28/19 • On schedule for submittal at end of March.
BR2 Capability Development | 23.06 | A37025 | INL-Evaluate SCK QA Process | Hammond MR | Jones W | 2/28/19 • Forecast to complete at end of April.
BR2 Capability Development | 23.06 | A37030 | INL/SCK-Conceptual Technical Descriptions of Fixturing & Handling Equipment | Hammond MR | Jones W | 2/28/19 • On schedule for submittal at end of March.
BR2 Capability Development | 23.06 | A37031 | SCK-Submit Agreement on Technical Desciptions of Fixturing & Handling Equipment | Hammond MR | Jones W | 2/28/19 • On schedule for submittal at end of March.
BR2 Capability Development | 23.06 | A37036 | SCK-Draft QA Plan Complete | Hammond MR | Jones W | 2/28/2019 Will be completed by March 28, 2019.
BR2 Capability Development | 23.06 | A37040 | INL/SCK-Formal QA Assessment & Certification (FY19) | Hammond MR | Jones W | 1/8/2019 In progress - see comments for activities A37020 and A37036
BR2 Capability Development | 23.06 | A37045 | BEA-Provide Conceptual Design of Channel Gap Probe to SCK | Hammond MR | Jones W | 1/8/2019 • INL is investigating options for channel gap probe activities. The UT team is planning a trip to SCK-CEN in February to discuss requirements.
BR2 Capability Development | 23.06 | A37055 | INL/SCK-Blister Furnace Design - 10311380L | Hammond MR | Jones W | 1/8/2019 • SCK-CEN is presenting their design package used for CEE I (safety review stage 1 (of three)) to INL on January 24, 2019, which should include blister furnace details.
BR2 Capability Development | 23.06 | A37056 | SCK-Submit Blister Furnace Fab Readiness Review Report | Hammond MR | Jones W | 1/8/2019 In progress - see comments for activities A37055 and A37056
BR2 Capability Development | 23.06 | A37060 | SCK-Fabricate Blister Furnace (FY19) - 10311380M | Hammond MR | Jones W | 1/8/2019 In progress - see comments for activities A37055, A37056, and A37060.
BR2 Capability Development | 23.06 | A37065 | INL/SCK-Assess & Design Pool side & PIE Equipment | Hammond MR | Jones W | 1/8/2019 • SCK-CEN is presenting their design package used for CEE I (safety review stage 1 (of three)) to INL on January 24, 2019, which should include poolside equipment details. Additional discussions will occur during the UT team visit in February 2019.
BR2 Capability Development | 23.06 | A37066 | SCK-Submit Final Assessment of Poolside Equipment | Hammond MR | Jones W | not started
BR2 Capability Development | 23.06 | A37071 | INL/SCK Design Reviews & Status Reports (FY19) | Hammond MR | Jones W | 2/6/19 • A formal meeting was held on January 21-22, 2019, to review the Committee for Evaluation of Experiments (CEE-I) report. SCK presented on the committee’s comments and concerns. INL presented on the MITR & NBSR conceptual element drawings. The design of MUSTANG R & P is proceeding as planned.
23.1.1.1.1.1.3 |  |  | HFIR Fuel Qualification
HFIR Fuel Qualification Design Inputs | 24.13 | A37751 | Prepare and Approve HFIR Fuel Qualification Plan | Shokes TE
HFIR Fuel Qualification Design Inputs | 24.13 | A37800 | Adjust HFIR Fuels Activity Plans | Jacobson JD | Cole J / Glagolenko I | 03/06/19 • The HFIR baseline has been established and approved FY19 work scope (HFIR Data Analysis/Modeling and FSP-HFIR and HFIR-DDE Scoping Study) has begun.
HFIR Fuel Qualification Design Inputs | 24.13 | A37800A | Adjust HFIR Fuels Activity Plans (Adjustment Feb 2019) | Shokes TE
FSP-HFIR | 24.14 | A44325 | FSP-HFIR HFIR Data Analysis/Modeling | Shokes TE
FSP-HFIR | 24.14 | A44331 | FSP-HFIR and HFIR-DDE Scoping Study | Shokes TE
FSP-HFIR | 24.14 | A44340 | FSP-HFIR Develop and Issue F&OR for FSP-HFIR | Shokes TE
FSP-HFIR | 24.14 | A44325M | FSP-HFIR HFIR Data Analysis/Modeling Complete | Shokes TE
FUTURE-HFIR | 24.18 | A93501.1 | Experiment Design (SCK) - Includes D1,D3,D4,D6, D7,D8, and D10 | Jacobson JD
FUTURE-HFIR | 24.18 | A93502 | Prepare and Issue Plate Specification (INL) | Jacobson JD | Jones W | 03/06/19 • Fuel profiles and drawings have been developed and are being sent to SCK-CEN to perform neutronics. • A draft of the fuel specification has been developed.
FUTURE-HFIR | 24.18 | A93503 | Prepare and Issue Test Plan (INL) | Jacobson JD | Jones W | 03/06/19 • As described in A93501, various configurations are being considered to accommodate either a typical (2x2) approach or a conservative (1-3-5) approach. The test plan is being written to accommodate either decision.
FUTURE-HFIR | 24.18 | A93505 | Perform Thermal Analysis (INL) | Jacobson JD | Jones W | 2/26/2019 • Not started • The need for this activity should be defined by SCK
FUTURE-HFIR | 24.18 | A93506 | Conduct Quality Assurance Oversight Review (INL) | Jacobson JD | Campbell J | 03/06/19 • A status was provided by SCK-CEN on January 24, 2019. INL suggested that SCK-CEN begin to work with INL QA to ensure that quality process/procedure meet INL requirements.
FUTURE-HFIR | 24.18 | A93620 | Irradiation Preparations and Oversight | Jacobson JD | Jones W | 2/26/2019 • Ongoing documentation development (FOR, TF&R, EEP, etc.)
FUTURE-HFIR | 24.18 | A93620A | Irradiation Preparations and Oversight | Jacobson JD
FUTURE-HFIR | 24.18 | A93679 | Prepare Characterization Plan | Jacobson JD | Jones W | 2/26/2019 not started
23.1.1.1.1.1.4 |  |  | Out-of-Pile Testing and Codes
Micro-Structural Characterization - Monolithic | 25.01 | A49590 | Perform Irradiated Fuel Characterization Micro Exam Low Dose AFIP-4 (5) | Bybee MJ | Keiser D
Micro-Structural Characterization - Monolithic | 25.01 | A49591 | Perform Irradiated Fuel Characterization Micro Exam Low Dose AFIP-4 (5) - Complete | Bybee MJ | Keiser D
Micro-Structural Characterization - Monolithic | 25.01 | A49600 | Complete Technical Report for Umo Impurity Affects (18) | Bybee MJ | Keiser D
Micro-Structural Characterization - Monolithic | 25.01 | A49601 | Complete Technical Report for Umo Impurity Affects (18) - Complete | Bybee MJ | Keiser D
Micro-Structural Characterization - Monolithic | 25.01 | A49605 | Perform Characterization of Gamma Stability Effects from AFIP-4 | Bybee MJ | Keiser D | 03/06/19 • SEM characterization on the first of eight specimens has commenced. Some of the eight specimens will also be characterized by EBSD and TEM.
Micro-Structural Characterization - Monolithic | 25.01 | A49606 | Perform Characterization of Gamma Stability Effects from AFIP-4 - Complete | Bybee MJ | Keiser D
Micro-Structural Characterization - Monolithic | 25.01 | A49610 | Complete Technical Report of Gamma Stability Effects AFIP-4 | Bybee MJ | Keiser D
Micro-Structural Characterization - Monolithic | 25.01 | A49611 | Complete Technical Report of Gamma Stability Effects AFIP-4 - Complete | Bybee MJ | Keiser D
Residual Stress | 25.1 | A51753 | Residual Stress Maintenance FY19 | Phillips AM | Cole J | Not started
Residual Stress | 25.1 | A51755 | Residual Stress - Fabrication, Assembly, and Verification for Wet Machining | Phillips AM | Cole J | 03/06/19 • Drawing updates to include the water drip system are nearly complete. Minor modifications recommended during the design review to make the system more easily repaired in the hot cell are ready to be started. For example, the eddy current sensor attachment will be changed to make it easy to replace the sensors in the hot cell.
Residual Stress | 25.1 | A51756 | Residual Stress - Fabrication, Assembly, and Verification for Wet Machining - Complete | Phillips AM | Cole J | Milestone
Residual Stress | 25.1 | A51758 | Residual Stress - Develop Phase II Qual Plan | Phillips AM | Cole J | Not started
Residual Stress | 25.1 | A51759 | Residual Stress - Develop Phase II Qual Plan - Complete | Phillips AM | Cole J | Milestone
Thermophysical Properties | 25.11 | A53575 | Assess Thermo Physical Data Needs | Bybee MJ | Schulthess, J | 03/06/19 • Final revisions to report PNNL-27255 "Thermal Conductivity Analysis of Irradiated U-Mo Alloy Fuels” are nearing completion. These revisions include a more robust treatment of Gaussian Error Propagation across the data set and corrections to inputs such as fission density of samples based on revised analysis provided by FQ. The values of irradiated thermal conductivity of U-10Mo is needed to support conversion analysis.
Bond Strength | 25.12 | A54688 | Maintain Laser Shock System FY19 | Phillips AM | Smith J | 03/06/19 • Investigation into the possible correlation between surface finish and velocity is temporarily on hold, pending test results from the Canadian system. If the Canadian system replicates INL results, then that indicates this is typical for this type of measurement. If their data does not match INL system data, additional investigation at INL will be warranted.
Fission Product Retention Testing | 25.04 | A55350 | FPR Draft Test Plan | Bybee MJ | Kwon, S | 03/06/19 • Equipment in HFEF is being surveyed for potential modification. • Two approaches, modifying DEOX furnace attaching monitoring system from FACS furnace and setting up a new furnace, were determined to be viable approaches. • Main investigation focus will be cost assessment versus accessible functions.
Fission Product Retention Testing | 25.04 | A55351 | FPR Draft Test Plan - Complete | Bybee MJ | Kwon, S
Engineering Scale Fuel Performance Modeling | 25.07 | A57050 | Integrated Fuel Performance Sensitivity Studies (FY19) | Phillips AM | Ozaltun H | 03/06/19 • Activities continue for task “effects of geometric parameters on performance”. Effects of selected geometric variables on plate performance are being investigated. A total of ten parameters were selected. The parameters are effects of zirconium thickness, fuel corner shapes, fuel offset, fuel flatness, size effects, fuel thickness, burred foil, fuel tilting, plate curvature, and foil waviness. Two parameters, “zirconium thickness” and “fuel corner shapes” are already completed and reported previously. Updates for four additional parameters are as follows: o Simulations have been completed for task “effects of fuel offset”. Plates with off-centered fuel within the cladding were evaluated. In particular, fuel zone was shifted incrementally to create a thinner cladding at the one side of the plate. Bounding cases were defined as minimum cladding thickness based on the specifications given in TEV2009. The results have indicated that preferential swelling occurs, when the fuel is off-center. No channel closure occurred for the cases that were evaluated during this work. o Simulations have been completed for task “effects of fuel flatness”. Performance of plates with slightly curved foil within a flat plate was evaluated. Two different sets were considered. The first case considered a curved foil located at the mid-plane, curved from mid-plane towards to one face, resulting a thinner cladding at the one side. The second case considered a curved foil that is perfectly centered within the cladding. Bounding cases were defined as point min cladding and bulk min cladding values that are specified in TEV2009. The results have indicated that when the fuel is curved, peak deformations occur at the thinner cladding side, and the plate tends to bow. Additional post-processing and analyses of the results are in progress. o Models for the second set of simulations are being generated for task “size effects”. Performance of plates with various length and width ratios are being evaluated. A full-length draft article was submitted. Additional cases are being evaluated while awaiting reviewer’s comments. o Activities have begun for task “Plate curvature”. Plates with various radius of curvature are being evaluated. The purpose of this work to investigate if a plate curvature has any effects on overall performance. The study also aims to address the concern stating that monolithic curved plates operating at high power may fail due to buckling. A simulation matrix is being created based on the bounding cases. An abstract entitled “Effects of Plate Curvature on the Performance of a U-10Mo Fuel Plates” was submitted to ASME IMECE.
Engineering Scale Fuel Performance Modeling | 25.07 | A57051 | Integrated Fuel Performance Sensitivity Studies (FY19) - Complete | Phillips AM | Ozaltun H
Engineering Scale Fuel Performance Modeling | 25.07 | A57450 | Integrated Fuel Performance Model Development (FY19) | Phillips AM | Ozaltun H | 03/06/19 • A journal article is being drafted for task “model development specific to U-Mo plate design”. The article documents performance assessment methodologies specific to the U-10Mo monolithic plate system, and provides important modeling considerations. • A journal article is being drafted for task “Effects of Coolant Channel Pressure”. The article documents if reactor coolant channel pressures are sufficient to suppress in reactor blister type failures. • Revisions on “Chapter 5: Material properties” and “Appendix C: Recommended Property Data” are on hold for task “Base Fuel Qualification Report Addendum”. Activities are awaiting the revised data set from PNNL.
Engineering Scale Fuel Performance Modeling | 25.07 | A57451 | Integrated Fuel Performance Model Development (FY19) - Complete | Phillips AM | Ozaltun H
Engineering Scale Fuel Performance Modeling | 25.07 | A58850 | ANL Modeling Support (FY19) | Phillips AM | Ozaltun H | 03/06/19 • Activities continue for the two tasks, “effect of operational parameters” and “effects of property related parameters”. Variables related to irradiation history and behavioral models are being evaluated. • Ten different parameters are being considered for task “effects of operational parameters”. The parameters are effects of mechanical constraints, fission profile, cooling rate, cooling conditions, power and burnup, bond strength, thermal cycling, residual stress state, fission rate, and flow induced vibration. • Simulations have been completed for task “effects of mechanical constraint”. Performance of plates with various mechanical constraints were evaluated. In particular, boundary conditions were changed to simulate different welding and plate attachment scenarios were evaluated. Analyses of the results continue. • The first set of simulations have been completed for task “effects of fission profile”. In this study, effects of fission gradients on thermo-mechanical performance were studied. A full-length draft article was submitted. Additional simulations are being performed, while awaiting reviewer’s comments. • Activities have begun for task “effects of cladding properties”. Effects of uncertainties in the cladding property data on accuracy of results are being evaluated. In particular, the cladding property data are being varied between the values reported in the literature. • The first set of simulations have been completed for task “effects of Zr-barrier properties”. In this study, effects of uncertainties in diffusion barrier property data on accuracy were studied. A full-length draft article was submitted. Additional simulations are being performed, while waiting reviewer’s comments.
Engineering Scale Fuel Performance Modeling | 25.07 | A59025 | FSI Method Integration (FY19) | Phillips AM | Ozaltun H
GTPA Flow Testing | 25.08 | A59465 | OSU HMFTF Standby #1 | Phillips AM | Jones W | Not started
| 25.08 | A59465A | OSU HMFTF Standby #1 - Adjustment: March 2019 | Phillips AM
GTPA Flow Testing | 25.08 | A59525 | OSU/INL - GTPA Test Data Analysis Report | Phillips AM | Jones W | 03/06/19 • A detailed review was performed of the draft Test Data Analysis Report submitted by Oregon State University (OSU). Comments were returned to OSU and are being addressed. Finalization in late May.
| 25.08 | A59525A | OSU/INL - GTPA Test Data Analysis Report - Adjustment - March 2019 | Phillips AM
GTPA Flow Testing | 25.08 | A59526 | OSU/INL - GTPA Test Data Analysis Report - Complete | Phillips AM | Jones W
GTPA Flow Testing | 25.08 | A59540 | INL - Issue GTPA Summary Report | Phillips AM | Jones W | Not started
GTPA Flow Testing | 25.08 | A59541 | INL - Issue GTPA Summary Report - Complete | Phillips AM | Jones W
GTPA Flow Testing | 25.08 | A59555 | OSU/INL - GTPA Plate Disposition | Phillips AM | Jones W | Not started
GTPA Flow Testing | 25.08 | A59565 | INL - Perform GTPA Analysis | Phillips AM | Jones W | 03/06/19 • Analysis of the GTPA flow test results is underway.
GTPA Flow Testing | 25.08 | A59575 | INL - Conduct FSI Modeling of GTPA | Phillips AM | Jones W | Not started
GTPA Flow Testing | 25.08 | A59605 | INL - GTPA Flow Test Complete | Phillips AM | Jones W
Microstructural Scale Fuel Performance Modeling | 25.14 | A63285 | INL Microstructural Modeling - FY19 Effects of Sec Phases & Interfaces & Recrystallization on Swelling Kinetics (PNNL) | Phillips AM | Beeler B | 3/25/2019 - Finalized and submited the manuscript “A Monte Carlo Model of Irradiation-Induced Recrystallization in Polycrystalline UMo Fuels” -Added the gas bubble nucleation process into the gas bubble evolution model in recrystallization zone because experiments show the evolution of gas bubble numbers
Microstructural Scale Fuel Performance Modeling | 25.14 | A63300 | INL Microstructural Modeling - FY19 DART Model of Swelling Consider Effect of Fission Rate & Density on Swelling (ANL) | Phillips AM | Beeler B | 3/25/2019 -Discussed the data inconsistency in the experimental data with INL and waiting for the release of an analysis report from INL. -Exploring the possibility of using ion irradiation data or dispersion fuel data to study fission gas behavior in monolithic fuel in the case that no in-pile data is available. -Tested the effect of gas atom resolution on U-Mo bubble swelling -Investigated the self-diffusion and Xe diffusion coefficients in U-Mo alloys using AIMD at different temperatures, 600K, 1000K, 1200K and 1400K
Microstructural Scale Fuel Performance Modeling | 25.14 | A63315 | INL Microstructural Modeling - FY19 Gas Diffusivity in Different Phases (INL) | Phillips AM | Beeler B | 3/25/2019 - Metadynamics simulations were initiated to accelerate Xe diffusion in high temperature bcc U in order to obtain quantifiable diffusion coefficients -Radiation driven diffusion of U, Mo and Xe was investigated in U10Mo systems from 100 K to 500 K, showing especially accelerated diffusion of Xe leading to nanonucleation of bubbles
Microstructural Scale Fuel Performance Modeling | 25.14 | A63335 | INL Microstructural Modeling - FY19 Irradiation Enhanced Creep (PNNL) | Phillips AM | Beeler B | 3/25/2019 -Reviewed the creep model in irradiated materials
Microstructural Scale Fuel Performance Modeling | 25.14 | A63345 | INL Microstructural Modeling - FY19 U-235 Uniformity: Variability Scoping Studies (ANL) | Phillips AM | Beeler B | 03/25/19 -The model will be built based on the assumption that the area with a higher U-235 concentration has a higher fission rate than other areas. -Generated microstructures of U-Mo alloy fuels with different U235 distribution configurations and U235 enriched secondary phases. -Tested effect of U235 inhomogeneity on U-Mo bubble swelling
Microstructural Scale Fuel Performance Modeling | 25.14 | A63365 | INL Microstructural Modeling - FY19 Phase Decomposition & Reversal & Their Effects on Recrystallization & Swelling (INL) | Phillips AM | Beeler B | 3/25/2019 -We investigated the atomic displacement and defect generation mechanism associated with the alpha to gamma transformation in U-Mo, through molecular dynamics simulation and crystallographic analyses. Our results suggest a non-uniform lattice distortion mechanism, with a combination of atomic shear and shuffle.
Microstructural Scale Fuel Performance Modeling | 25.14 | A63316 | INL Microstructural Modeling - FY19 Gas Diffusivity in Different Phases (INL) - Complete | Phillips AM | Beeler B
Microstructural Scale Fuel Performance Modeling | 25.14 | A63366 | INL Micro Modeling - FY19 Phase Decomp & Reversal & Their Effects on Recrystallization & Swelling (INL) - Complete | Phillips AM | Beeler B
Microstructural Scale Fuel Performance Modeling | 25.14 | A63380 | INL Historical Samples Characterization Data Assessment (INL) (FY19) | Phillips AM | Beeler B
Microstructural Scale Fuel Performance Modeling | 25.14 | A63381 | INL Historical Samples Characterization Data Assessment (INL) (FY19) - Complete | Phillips AM | Beeler B
Microstructural Scale Fuel Performance Modeling | 25.14 | A63395 | INL Microstructural Modeling - FY19 Complete Microstructural Modeling Summary Report (INL) | Phillips AM | Beeler B
Microstructural Scale Fuel Performance Modeling | 25.14 | A63396 | INL Microstructural Modeling - FY19 Complete Microstructural Modeling Summary Report (INL) - Complete | Phillips AM | Beeler B
Microstructural Scale Fuel Performance Modeling | 25.14 | A63398 | INL Historical Samples Characterization Data Assessment Summary Report (INL) (FY19) | Phillips AM | Beeler B
Microstructural Scale Fuel Performance Modeling | 25.14 | A63399 | INL Historical Samples Characterization Data Assessment Summary Report (INL) (FY19) - Complete | Phillips AM | Beeler B
23.1.1.1.1.1.5 |  |  | Fuel Qualification Support
Irradiated UMo Experiment Disposal | 26.02 | A59935 | FY19 Irradiated UMo Experiment Disposal | Kunz TJ | Kunz T
General Equipment and Maintenance | 26.03 | A60115 | Service Contracts and Equipment Maintenance (FY19) | Kunz TJ | Kunz T
UT Equipment | 26.05 | A63424 | FY18 C/O CGP - Perform Testing on Channel Gap Probe Wands | Johnson MP | Smith J | 03/06/19 • Received information from the vendor and will perform software assessment.
UT Equipment | 26.05 | A65000 | INL Maintain Existing CGP Equipment (Support MP-1 & MP-2 Experiments) | Johnson MP | Smith J | 2/27/19 • On Track M. Johnson
UT Equipment | 26.05 | A65025 | INL Develop UT Equipment debugging Laboratory | Johnson MP | Smith J | 03/06/19 • Continue to enable ultrasonic development laboratory capabilities to support prototyping. Assess what other UT devices and laboratory space can be resourced.
UT Equipment | 26.05 | A65050 | Develop INL and BR2 Draft Mark III Tool Conceptual | Johnson MP | Smith J | 03/06/19 • Acquiring information from experiment PIs, Program, and facilities (INL and BR2) to complete FORs. • Continuing to develop conceptual prototypes.
UT Equipment | 26.05 | A65075 | Review INL & BR2 Mark III Tool Conceptual Design report | Johnson MP | Smith J | 2/27/19 • On Track M. Johnson
UT Equipment | 26.05 | A65100 | Finalize and Issue INL & BR2 Mark III Tool Conceptual Design report | Johnson MP | Smith J | 2/27/19 • On Track M. Johnson
UT Equipment | 26.05 | A65101 | Finalize and Issue INL & BR2 Mark III Tool Conceptual Design report - Complete | Johnson MP | Smith J | 2/27/19 • On Track M. Johnson
UT Equipment | 26.05 | A65125 | INL Procure Subcontractor to design, fabricate, and qualify Mark III Tool | Johnson MP | Smith J | 11/1/18 TBD
23.1.1.1.1.1.8 |  |  | Fuel Qualification Integration
FQ Project Management | 40.01 | A62764 | Fuel Qualification Project Management (FY19) | Rosenberg KE | Rosenberg K
FQ Risk Management | 40.02 | A63441 | FQ - INL Risk Management Implementation (FY19) | Rosenberg KE | Ohene Opare E | 03/06/19 • Fourteen (14) risks out of 83 risks previously closed risks were reopened and assigned new risk IDs and were recharacterized. • Twelve (12) out of 15 additional risks identified after the Belgium meeting by SMEs were characterized and transferred to the CRR. • Relabeled FSP-HFIR-mid and FSP-HFIR-high with their new labels as FSP-HFIR and DDE-HFIR names respectively. • Ensured that changes in scheduled activity IDs and descriptions for two BCR proposals did not adversely affect the integrity and relationship mappings between risks and activities in the risk registry. • A meeting was held with other Pillar Risk Managers concerning cross cutting risks about the possibility and consequence of Belgium authorities delaying approval of shipping casts for fuel transfer to BR2. The risk has been captured in the tracking spreadsheet and awaiting resolution before being transferred into CRR.
FQ Quality Assurance | 40.03 | A63456 | FQ - Base Fuel Qualification Quality Assurance (FY19) | Rosenberg KE | Campbell J
FQ Technical Integration | 40.04 | A64001 | Fuel Qualification Technical Integration (FY19) | Rosenberg KE | Rosenberg K
Dispersion
EMPiRE | 50.01 | A90100 | FY 19 EMPIrE Experiment Oversight | Bybee MJ | Glagolenko I
EMPiRE | 50.01 | A90150 | FY 19 EMPIrE HFEF Equipment Preparations | Bybee MJ | Glagolenko I
EMPiRE | 50.01 | A90170 | EMPIrE As-Run Analysis | Bybee MJ | Glagolenko I | 2/6/19 • The project is running as-run models. Completed 162-B and running the 164-A. An ECAR is forecasted to be complete in June 2019.
EMPiRE | 50.01 | A90250 | EMPIrE Fresh Fuel Characterization | Bybee MJ | Glagolenko I
EMPiRE | 50.01 | A90275 | EMPIrE Non-Destructive PIE Batch 1 (16 Plates) | Bybee MJ | Glagolenko I | 03/06/19 • Immersion density measurements have been completed. Precision Gamma Scanning is ongoing.
EMPiRE | 50.01 | A90310 | EMPIrE Non-Destructive PIE Batch 2 (28 Plates) | Bybee MJ | Glagolenko I | 03/06/19 • Immersion density measurements have been completed. Precision Gamma Scanning is ongoing.
EMPiRE | 50.01 | A90320 | EMPIrE Non- Destructive PIE - Complete | Bybee MJ | Glagolenko I
EMPiRE | 50.01 | A90330 | EMPIrE Monolithic (C2TWP) Plate Shipment Support (FY 19) | Bybee MJ | Glagolenko I
EMPiRE | 50.01 | A90340 | EMPIrE Destructive PIE Batch 1 (3 Plates) | Bybee MJ | Glagolenko I
EMPiRE | 50.01 | A90350 | FY19 EMPIrE Destructive PIE Batch 2 (6 Plates) | Bybee MJ | Glagolenko I
EMPiRE | 50.01 | A90375 | FY 19 EMPIrE Waste Disposition | Bybee MJ | Glagolenko I
EMPiRE | 50.01 | A90390 | FY 19 EMPIrE Thermal Conductivity Measurements | Bybee MJ | Glagolenko I
EMPiRE | 50.01 | A90400 | EMPIrE 50% Destructive PIE - Complete | Bybee MJ | Glagolenko I
HERACLES Support | 50.02 | A92500 | HERACLES FDEG Support | Hammond MR | Glagolenko I | 1/8/19 • An FDEG Meeting will be held in Brussels Belgium on January 14-15, 2019. The meetings will focus on irradiation vehicle/basket design and other technical topics.
HERACLES Support | 50.02 | A92510 | HERACLES Technical & Strategic Committee Support | Hammond MR | Glagolenko I | 1/8/19 • HERACLES Technical & Strategic Committee meetings will be held in Brussels Belgium on January 16-17, 2019.
HERACLES Support | 50.02 | A92520 | SCK-CEN PhD Student Contract (60K/year) | Hammond MR | Glagolenko I
HERACLES Support | 50.02 | A92530 | Write Report on Powder Characterization | Hammond MR | Glagolenko I
Microstructural Characterization | 50.03 | A92600 | Dispersion Micro Characterization Sample Prep | Hammond MR | Keiser D | 1/8/19 • Historical samples have been shipped to the IMCL facility for analysis and work is being performed on those samples (High fission rate & UMo content plates).
Microstructural Characterization | 50.03 | A93100 | Detailed Microstructural Characterization of Irradiated Fuel | Hammond MR | Keiser D | 2/6/19 • Sample prepping began in the SSPA on January 29, 2019. Samples should be polished by the mid-week and FIB/SEM the week of February 4, 2019.
HERACLES Tech Support | 50.04 | A95200 | Program Integration Support | Hammond MR | Glagolenko I
HERACLES Tech Support | 50.04 | A95300 | FMEG Support | Hammond MR | Glagolenko I
HERACLES Tech Support | 50.04 | A95400 | Reject Plate Shipments | Hammond MR | Glagolenko I
HERACLES Tech Support | 50.04 | A95410 | KAERI Contract | Hammond MR | Glagolenko I | 1/8/19 • HAMP 2 & 3 Irradiations started second irradiation cycles in December. HAMP 2 is forecast to complete irradiation by December 2019, and HAMP 3 is forecast to complete irradiation by December 2020. PIE is forecasted to be complete by December 2021.

## Completed
Work Package Title | LWBS | Activity ID | Activity Name | PM | PI | Monthly Input
Mini Plate 1 (MP-1) | 22.18 | A20400 | MP-1 Pre-Irradiation Material Properties Tensile Testing | Meacham N | Marshall M/Schulthess, J | 12/1/18 • Experimental work to perform tensile tests for mechanical properties of bare foil material from the MP-1 fabrication effort has been completed. The tests included foils rolled to 8.5 mil and 25 mil thicknesses. Tests were conducted both longitudinal and transverse in the foil relative to the rolling direction, and were performed at a range of temperatures to evaluate the impact on the mechanical properties. Data analysis has begun and post-testing dimensional inspections are being scheduled. This data supports establishment of the baseline material properties of the MP-1 as-fabricated material.
Mini Plate 1 (MP-1) | 22.18 | A20401 | MP-1 Pre-Irradiation Material Properties Tensile Testing - Complete | Meacham N | Marshall M/Schulthess, J
Mini Plate 1 (MP-1) | 22.18 | A20402 | MP-1 Pre-Irradiation Material Properties Residual Stress (LEU) | Meacham N | Marshall M/Schulthess, J | 1/7/19 • MP-1 Pre-Irradiation Material Properties Residual Stress (LEU) testing was completed on December 16, 2018, one week ahead of the planned December 21, 2018, milestone due date.
Mini Plate 1 (MP-1) | 22.18 | A20404 | MP-1 Pre-Irradiation Material Properties Thermo Physical | Meacham N | Marshall M/Schulthess, J | 03/06/19 • Testing of fresh fuel foil samples from MP-1 fabricated material has been completed. This includes performing laser flash analysis (thermal diffusivity), differential scanning calorimetry (specific heat capacity), dilatometer measurements (thermal expansion), and immersion density measurements. The resultant analysis of the data will provide baseline thermal conductivity data of the as-fabricated MP-1 material. Data analysis is currently ongoing.
Mini Plate 1 (MP-1) | 22.18 | A20406 | MP-1 Pre-Irradiation Material Properties Residual Stress (LEU) - Complete | Meacham N | Marshall M/Schulthess, J
Mini Plate 1 (MP-1) | 22.18 | A20407 | MP-1 Pre-Irradiation Material Properties Thermo Physical - Complete | Meacham N | Marshall M/Schulthess, J
Full Size Plate 1 (FSP-1) | 22.16 | A23313 | FSP-1 Final Re-Design (INL) | Meacham N | Marshall M | 03/06/19 • Final redesign was completed on February 15, 2019. The final design review is scheduled to kick-off in March 2019.
Full Size Plate 1 (FSP-1) | 22.16 | A23314 | FSP-1 Final Re-Design (INL) - Complete | Meacham N | Marshall M | 11/1/18 • The final design is complete. Documents are being revised, checked, and finalized in preparation for the design review. Targets are being met. Safety analysis were performed.
Base Fuel Qualification Report | 22.14 | A30255 | Update Base Fuel Qualification Plan | Johnson MP | Cole J | 03/06/19 • Addressed additional comments from DOE-NNSA on the U-Mo Monolithic Fuel Qualification Plan.
MITR Design Demonstration Experiment (DDE) | 23.01 | A30820 | MITR-DDE Review Inputs from F&OR-158 | Jacobson JD | Jones W | 03/06/19 COMPLETE • The logic ties for this activity have been modified. The design authority receives documents from RC and updates FOR-158 as needed. These updates occur every six months.
MITR Design Demonstration Experiment (DDE) | 23.01 | A30825 | MITR-DDE Review Inputs from F&OR-158 | Jacobson JD | Jones W | 03/06/19 COMPLETE • The logic ties for this activity have been modified. The design authority receives documents from RC and updates FOR-158 as needed. These updates occur every six months.
MITR Design Demonstration Experiment (DDE) | 23.01 | A30825A | MITR-DDE Review Inputs from F&OR-158 (Adjustment) | Jacobson JD | Jones W | Adjustment activity, no need to report on this.
HFIR | 24.13 | A37800 | Adjust HFIR Fuels Activity Plans | Jacobson JD | Cole J / Glagolenko I | 2/26/19 • The HFIR baseline has been established and approved FY19 work scope has begun.
BR2 Capability Development | 23.06 | A37005 | INL-Provide DDE MITR & NBSR Conceptual Element Design | Hammond MR | Jones W | 1/8/19 • The MITR & NBSR conceptual element drawings are complete and will be submitted into the INL vendor data system in January and presented at the CEE Phase 1 design meetings at SCK-CEN on January 21, 2019.
BR2 Capability Development | 23.06 | A37011 | INL/SCK-Conceptual Design CEE Phase I Complete | Hammond MR | Jones W | 1/30/2019 Held formal meeting on January 21-22 to review the Committee For Evaluation of Experiments (CEE-I) report. SCK presented on the committees comments and concerns. INL presented on the MITR & NBSR conceptual element drawings. The design of MUSTANG R & P is proceeding as planned.
FUTURE-HFIR | 24.18 | A93500 | Issue Contract with SCK (INL) | Jacobson JD | Jones W | COMPLETE
FUTURE-HFIR | 24.18 | A93501 | Experiment Design (SCK) - Includes D1,D3,D4,D6, D7,D8, and D10 | Jacobson JD | Jones W | 03/06/19 • The project name has been changed from COBRA-HFIR to FUTURE-HFIR. • Bi-weekly teleconferences are held between SCK-CEN, INL, FF, FQ, CC, and BWXT. Minutes were collected and distributed to all attendees • A decision was made to use the flat-plate basket design for the experiment (FUTURE-5 basket). • Considering whether the five slots in the basket should be loaded in a 1-3-5 configuration (every other plate is fuel), or a 2x2 configuration (similar to previous SEMPER-FI, E-FUTURE tests). • Thermal Conductivity measurement options are being evaluated by SCK. • Flux wires are not currently incorporated in the FUTURE-5 basket. • The shipping container certification revision is occurring in both US and Belgium.
FUTURE-HFIR | 24.18 | A93507 | Final Design Verification & Acceptance (INL) | Jacobson JD | Jones W | 2/26/2019 • This is a acceptance of the contractor design. This will begin after the SCK-CEN design is complete.
FUTURE-HFIR | 24.18 | A93508 | Design Complete | Jacobson JD | Jones W | 2/26/2019 This is a milestone and will only be statused when complete
Micro-Structural Characterization - Monolithic | 25.01 | A49595 | Characterize UMo Impurity Affects (18) | Bybee MJ | Keiser D | 2/6/19 • All six planned specimens have been characterized by scanning electron microscopy (SEM) to study the possible impacts of impurity on the irradiation behavior of monolithic U-Mo fuels. Two of these six specimens are fresh fuel specimens, and the other four are irradiated fuel specimens (fission density varies from 3 to 5 x1021 fission/cc). These specimens are from the RERTR-12 (mini-plates) and AFIP-6MKII (full size fuel plates) experiments. Data reduction has commenced, and a summary report will be drafted.
Micro-Structural Characterization - Monolithic | 25.01 | A49596 | Characterize Umo Impurity Affects (18) - Complete | Bybee MJ | Keiser D
Residual Stress | 25.1 | A51745 | INL Residual Stress System Development Report | Phillips AM | Cole J | 12/1/18 • Complete.
Residual Stress | 25.1 | A51746 | INL Residual Stress System Development Report - Complete | Phillips AM | Cole J | Complete
Residual Stress | 25.1 | A51752 | Residual Stress - Design for Remote Wet Machining | Phillips AM | Cole J | 2/28/19 • COMPLETE
GTPA Flow Testing | 25.08 | A59450 | OSU/INL - GTPA PFFR Testing & Analysis | Phillips AM | Jones W | 03/06/19 • The flow test data is being archived at INL, which will conclude this activity. The data cover sheet was circulated and signed.
GTPA Flow Testing | 25.08 | A59451 | OSU/INL - GTPA PFFR Testing & Analysis - Complete | Phillips AM | Jones W
GTPA Flow Testing | 25.08 | A59452 | OSU/INL - GTPA PFFR Testing & Analysis - Complete | Phillips AM | Jones W
GTPA Flow Testing | 25.08 | A59495 | OSU/INL - GTPA UPF Testing & Analysis | Phillips AM | Jones W | 03/06/19 • An ECAR was drafted that summarizes the Ultimate Plate Failure (UPF) flow tests. This ECAR and its associated results will help support the 2018 addendum to the USHPRR Base Fuel Qualification report. The document is in technical checked.
GTPA Flow Testing | 25.08 | A59496 | OSU/INL - GTPA UPF Testing & Analysis - Complete | Phillips AM | Jones W
GTPA Flow Testing | 25.08 | A59535 | INL - Evaluate Flow Rate Discrepancies Uncommitted Carryover | Phillips AM | Jones W | COMPLETE
EMPiRE | 50.01 | A90175 | EMPIrE Cooling and Shipping (32 Plates) | Bybee MJ | Glagolenko I | 2/6/19 • All Empire shipments have been completed and non-destructive exams are ongoing in HFEF.
EMPiRE | 50.01 | A90200 | EMPIrE PIE Preparations Augmentation | Bybee MJ | Glagolenko I
EMPiRE | 50.01 | A90276 | Perform Prellim Visual Insp on First EMPIrE Shipment and Start NDE PIE - Complete | Bybee MJ | Glagolenko I | 11/1/18 • This activity is complete. Completed 10/11/2018
EMPiRE | 50.01 | A90300 | EMPIrE Channel Gap Report Development | Bybee MJ | Glagolenko I
Microstructural Characterization | 50.03 | A92599 | Agree characterization and PIE plan with HERACLES and U.S. team | Hammond MR | Keiser D
MURR Design Demonstration Experiment (DDE) | 23.02 | A32290 | MURR DDE Review Inputs from F&OR-158 | Jacobson JD | Glagolenko, I | 03/06/19 COMPLETE • The logic ties for this activity have been modified. The design authority receives documents from RC and updates F&OR -158 as needed. These updates occur every 6 months.
MURR Design Demonstration Experiment (DDE) | 23.02 | A32295 | MURR DDE Review Inputs from F&OR-158 (ANL) | Jacobson JD | Glagolenko, I | 03/06/19 COMPLETE • The logic ties for this activity have been modified. The design authority receives documents from RC and updates F&OR -158 as needed. These updates occur every 6 months.
NBSR Design Demonstration Experiment (DDE) | 23.03 | A33840 | NBSR-DDE Review Inputs from F&OR-158 | Jacobson JD | Jones W | 03/06/19 COMPLETE • The logic ties for this activity have been modified. The design authority receives documents from RC and updates F&OR -158 as needed. These updates occur every 6 months.