## FY19
Sponsor | Level | Due Date | Description | Funding ($K) | Responsible Party | Completion | Responsible Individual
AFC | M? | 2019-09-30 | Couple Oxygen/Actinide/Porosity/Temperature/Displacements in MOX fuel simulation | 500 | EST |  | Novascone | x
CASL | L2 | 2019-03-29 | Demonstration of TRACE/Bison LOCA capability for LWR and ATF fuel | 200 | EST |  | Gardner
CASL | L3 | 2019-04-30 | Bison Solution Verification Tool and Demonstration | 25 | EST |  | Gardner
CASL | L3 | 2019-05-31 | LOCA Challenge Problem Final Report | 50 | EST |  | Williamson
CASL | L3 | 2019-06-30 | Improvements in Bison robustness and performance | 350 | CMT |  |  | x
CASL | L3 | 2019-07-30 | ATF material model development and validation for priority fuel concepts | 350 | EST |  | Gamble | x
CASL | L3 | 2019-08-30 | ATF material model development and validation for priority cladding concepts | 300 | EST |  | Gamble
CASL | L3 | 2019-08-30 | Improve Bison validation base and documentation for LWR fuel | 250 | EST |  |  | BWS note: I think this will be covered by both EST and CMT, and led by Pitts
CASL | L3 | 2019-09-30 | NRC engagement on ATF fuel | 120 | EST |  | Williamson | x
CASL | ?? | ??? | Excore/Grizzly demonstration | 150 (tentative) | CMT |  | Spencer
LWRS | M2 | 2019-09-30 | RPV and concrete development | 280 (tentative) | CMT |  | Spencer
NEAMS | M3 | 2019-01-27 | Implement unit cell volumetric swelling model for metallic fuel | 200 | EST |  | Casagranda | x
NEAMS | M3 | 2019-06-20 | Perform initial assessment of multi-scale modeling needs and define road map for implementing lower length scale informed swelling model for metallic fuel Implement lower length scale informed swelling model for metallic fuel | 100 | EST |  | Novascone
NEAMS | M2 | 2019-06-21 | Implement failure models and statistical treatment to compute failure probability for particle fuel | 400 | CMT |  | Jiang
NEAMS | M3 | 2019-07-18 | Convert existing validation cases to new Bison documentation system | 100 | EST |  |  | x | Steve Bajorek's validation plan, lit review and talk to Blaise.
NEAMS | M2 | 2019-08-15 | Develop validation plan for metallic fuel and run additional validation cases | 250 | EST |  | Novascone
NEAMS | M3 | 2019-08-30 | Develop validation plan for particle fuel and run additional cases | 200 | EST
NEAMS | M2 | 2019-09-30 | MARMOT modeling of swelling in U-Zr and integration into BISON | 500 | LLS |  | Aagesen, Jokisaari
NEAMS | M3 | 2019-09-30 | XFEM crack propagaion for 3D structural component models | 150 | CMT |  | Spencer
NEAMS | M3 | 2019-06-30 | Implement and assess the grain growth and fracture models in BISON | 200 | LLS |  | Wen Jiang, Biswas
NEAMS | M3 | 2019-07-30 | Atomistic calculations of material parameters for swelling and redistribution models in U-Zr fuel | 250 | LLS |  | Beeler
NEAMS | M2 | 2019-08-30 | CALPHAD calculations of lanthanide and element inter-diffusion between U-Zr fuel and steel cladding | 250 | LLS |  | Chao Jiang
SciDAC | M3 | 2019-09-30 | Modeling Intra-granular Fission Gas Bubble Evolution in Uranium Dioxide during Transients | 400 | EST |  | Pastore
3395
NEAMS activities |  | Due Date | Description | Funding ($K) | Responsible Party | Completion | Responsible Individual
|  | 2019-03-30 | Provide training and support material model development | 100 | EST/CMT |  |  | x
|  | 2019-04-30 | Adapt XFEM to simulate moving material interface | 50 | CMT |  | Tompkins
|  | 2019-05-30 | Improve frictional contact | 150 | CMT |  | Lindsay | x
|  | 2019-08-30 | Support MW-scale reactor development and analysis | 200 | ? |  |  | x
|  | 2019-09-15 | Improve code robustness and plan/implement rigorous material model testing for metallic fuel | 250 | EST |  | Novascone | x
|  | 2019-09-30 | User training and support | 50 | EST |  | Novascone | x
|  | 2019-04-28 | Develop, commit, and test high-temperature creep/plasticity models | 150 | CMT |  | Spencer | x
|  | 2019-09-30 | Implementation of Reduced-order model of VPSC into MOOSE-based Codes | 300 | CMT |  | Spencer | x
|  | 2019-09-30 | Increase the assessment of the mechanistic thermal conductivity model in Bison and evaluate the contribution of solid fission products and point defect | 100 | LLS |  | Zhang
|  | 2019-09-30 | Improve the MARMOT capability for nucleation and swelling and commitments | 120 | LLS |  | Schwen
6215

## FY18
Sponsor | Level | Due Date | Description | Responsible Party | Completion | Responsible Individual
CASL-FMC | ACT (#2239) | 43373 | FMC Deputy (75k) |  |  | Williamson
CASL-FMC | ACT (#2447) | 43373 | Support for Bison users (100k) | EST |  | Gardner
CASL-FMC | L3 (#2448) | 43371 | Evaluation of solver and time-stepping options (100k) | CMDT/EST |  | Spencer
CASL-FMC | L3 (#2165) | 43358 | Demonstrate PWR large break LOCA capability (225k) | EST |  | Gardner
CASL-FMC | L3 (#2171) | 43343 | Axial fuel relocation (100k) | EST |  | Gamble
CASL-FMC | L3 (#2153) | 43343 | RIA Experimental benchmark (200k) | EST |  | Williamson
CASL-FMC | L3 (#2168) | 43280 | LOCA Experimental benchmark (200k) | EST |  | Williamson
CASL-FMC | L3 (#2175) | 43280 | Update BISON documentation (50k) | CMDT |  | Pitts
CASL-FMC | L2-DOE (#2093) | 43266 | Improve code robustness and speed (300k) | CMDT/EST |  | Spencer
CASL-FMC | L3 (#2129) | 43251 | XFEM material interface tracking (100k) | CMDT |  | Jiang
CASL-FMC | L3 (#2155) | 43250 | Transient fission gas behavior (100k) | EST |  | Pastore
CASL-FMC | L3 (#2125) | 43159 | Verify and Validate 1.5D capability (75k) | CMDT/EST |  | Casagranda
CASL-FMC | L3 (#2170) | 43130 | Radial fuel relocation (150k) | CMDT |  | Jiang
FCRD | L2 | 43373 | Issue status report on BISON development for fast reactor MOX | CMDT/EST |  | Novascone
LWRS | L3 | 43373 | Concrete Degradation Modeling | CMDT |  | Spencer
LWRS | L2 | 43281 | Reactor Pressure Vessel Fracture Modeling | CMDT |  | Spencer
NEAMS-BISON | M3 | 43373 | Conduct validation studies and issue updated BISON validation report | CMDT/EST |  | Gardner
NEAMS-BISON | M3 | 43373 | Investigate ATF concepts including SiC-SiC, Uranium Silicide, Cr-doped UO2 | EST |  | Gamble
NEAMS-BISON | M2 | 43373 | Release BISON with Initial Metallic Fuel Performance Capability | CMDT/EST |  | Casagranda/Novascone
NEAMS-BISON | M2 | 43310 | RIA Demonstration with Experimental Assessment | EST |  | Pastore
NEAMS-BISON | L3 | 43156 | Improve LWR fuel rod mechanics models | CMDT |  | Spencer
SciDAC | L3 | 43373 | Develop and implement in BISON a new engineering-scale intra-granular fission gas model | EST |  | Pastore

## FY17
Sponsor | Level | Due Date | Description | Responsible Party | Completion
CASL-FMC | L3 | 2016-12-31 | Develop and Initially Demonstrate BISON 1.5D Capability for LWR Fuel (100k) [#1688] | CMDT | 2017-01-11
NEAMS-ATF | M4 | 2016-12-31 | Coordinate model development and experimental design with AFC | ESNFST | 2016-12-22
CASL-PHI | L3 | 2017-03-30 | Review of Bison usage in VERA (100k) [#1766] | ESNFST | 2017-03-30
CASL-FMC | L3 | 2017-03-31 | Extended XFEM/PCMI Capabilities (125k) [#1678] | CMDT | 2017-03-30
NEAMS-BISON | M2 | 2017-05-31 | LOCA Demonstration with Experimental Assessment (IFA 650.10) | ESNFST | 2017-05-19
CASL-FMC | L3 | 2017-06-30 | Verification and Validation of BISON 1.5D Capability (100k) [#1682] | CMDT | 2017-07-11
NEAMS-BISON | M2 | 2017-06-30 | UFD Proof-of-Concept Demonstration | ESNFST | 2017-06-30
CASL-PHI | L3 | 2017-07-15 | Baseline MOOSE/Bison support (100k) [#1809 - 100k MOOSE/100k Bison/50k LibMesh] | ESNFST/MOOSE | 2017-07-15
NEAMS-BISON | M3 | 2017-07-30 | Oxide Fuel Mechanics in 3D | ESNFST/CMDT | 2017-07-29
CASL-FMC | L2 | 2017-07-31 | BISON capability development for accident analysis (250k) [#1652] | ESNFST | 2017-07-31
NEAMS-ATF | M4 | 2017-07-31 | Coordinate multiscale FeCrAl modeling | ESNFST
NEAMS-ATF | M4 | 2017-07-31 | Coordinate multiscale U3Si2 modeling | ESNFST
CASL-FMC | L3 | 2017-08-15 | Develop a RIA experimental benchmark for BISON (250k) [#1685] | ESNFST
NEAMS-BISON | M3 | 2017-08-30 | Code and Documentation Cleanup | ESNFST/CMDT
NEAMS-ATF | M2 | 2017-08-31 | Deliver FeCrAl material modeling capability | ESNFST
NEAMS-ATF | M2 | 2017-08-31 | Deliver U3Si2 material modeling capability | ESNFST
CASL-FMC | L4 | 2017-09-01 | Support load following task - UIUC Test Stand (50k) [#1734] | ESNFST
CASL-FMC | L4 | 2017-09-01 | FMC Leadership (50k) [#1735] | ESNFST
CASL-FMC | L2 - DOE Reportable | 2017-09-15 | Develop a LOCA experimental benchmark for BISON (300k) [#1655] | ESNFST
CASL-FMC | L2 | 2017-09-29 | Contact Improvements for PCMI (400k) [#1656] | CMDT/MOOSE
CASL-FMC | L3 | 2017-09-29 | Fuel Radial Relocation (200k) [#1687] | CMDT
FCRD | n/a | 2017-09-30 | Evaluation and preliminary integration of relevant metal fuel models (including anisotropic swelling) for simulating the EBR2 X447 experiment (or other similar experiment) that can serve as the basis for a journal paper | ESNFST
FCRD | n/a | 2017-09-30 | Development of models and methods for simulating redistribution of porosity, oxygen and minor actinides from low to high burnup | ESNFST
NEAMS-ATF | M2 | 2017-09-30 | Deliver ATF evaluation report to AFC | ESNFST
NEAMS-BISON | M3 | 2017-09-30 | Perform validation studies and issue updated BISON validation report | ESNFST
NEAMS-BISON | M3 | 2017-09-30 | User Training and Support | ESNFST/CMDT

## Data
CASL-FMC | CMDT
CASL-PHI | CMDT/EST
FCRD | CMDT/MOOSE
LDRD | EST
NEAMS-BISON | EST/MOOSE
NEUP
LWRS
SciDAC